## Slide 1
JEV-TRADING — PROPOSED PROJECT PLAN
Extend MVP to P8 / Shadow Live | 2026-09-23
Scope: P7 iterate (threshold grid, cost-aware policy, down-model) → P8 shadow validation → Tiny-live proposal.
Source: workspace README / IMPLEMENTATION_PLAN / docs / contracts / execution / backtest / data / scripts

## Slide 2
PROJECT OVERVIEW & CURRENT STATUS
• Pipeline: Live feed → State (16 features) → Quant (LightGBM AUC 0.637, ECE 0.01) → Jev(mock) → Policy → Risk (absolute) → PaperExec → JSONL replay
• Data: 2,629,440 1m BTCUSDT perp rows [2021–2026], contiguous, 0 dupes
• P0–P6 ✅ | P7 FAIL (net −0.35% at p_up≥0.55; 2–3× fees deepen) | P8 shadow validated live (4 bars, 0 entries consistent, latency 634–1548ms)
• Next: 4–7 weeks to iterate thresholds / validate / propose promotion

## Slide 3
ARCHITECTURE — 6-LAYER FAST LOOP
L1 Data Ingest (Binance REST 1200w/min + WS + Kalshi/Polymarket)
L2 State Engine (backward-only 16 feats + build_state_dict)
L3 Quant Engine (LightGBM; y_up_15 / y_dn_15; threshold 0.0014 frozen)
L4 Jev / Mock Client (5 MVP yes/no; TypeSafe protocol; position-aware P7)
L5 Policy + Risk (threshold policy + audit reasons; deterministic RiskKernel; halt/gate)
L6 Paper Execution (PaperTrader; next-open; replayable JSONL; zero real money)

## Slide 4
TOOL RESEARCH — ML, DATA & APIs (Monid + Specs + Cost)
LightGBM — MIT / Microsoft / AUC 0.637 / ECE 0.01 / CPU ~1–3min train / $0
NumPy/Pandas — BSD / 2.6M rows / RAM 4–8GB / $0
Binance REST — Free / 1200 weight/min / 1m klines / $0
Binance WS — Free / real-time / ~5 conn/min / $0
Polymarket/Kalshi — Free read / PM_COLUMNS / warn-and-continue / $0
Scikit-learn — BSD / baselines A–E / $0

## Slide 5
TOOL RESEARCH — UI, EXECUTION & OFFICE CLI
Streamlit — Apache 2 / dashboard / free tier + ~$5/mo paid / $0 local
PaperTrader (execution/) — Project / zero real money / JSONL replay / 634–1548ms/bar / $0
Backtest Simulator — Project / BAR→STATE→QUANT→JEV→POLICY→RISK→ORDER / CPU hours / $0
officecli v1.0.151 — CLI / .xlsx/.pptx create/edit/batch / $0 (this deliverable)
Python 3.12 / PyArrow / requests — PSF/Apache / $0
Monitoring: Prometheus/Grafana self-host ~$15/mo or Datadog ~$30/mo

## Slide 6
RESOURCES & HARDWARE RECOMMENDATIONS
Dev / Shadow: 8-core CPU / 32GB RAM / 1TB NVMe (existing) / $2,000 one-time
Shadow Server: AWS t3.medium (2 vCPU / 4GB) / ~$30/mo / us-east-1
Tiny-Live (post-P7): AWS c6i.large (2 vCPU / 4GB) / ~$62/mo / 100GB SSD
Storage: Local 1TB + S3 500GB backup / ~$11/mo
Network: Broadband + static IP / VPN / ~$10/mo
GPU (deferred): NVIDIA T4 / A10 / ~$250–600/mo ONLY if P7 justifies deep model
Total Shadow: ~$65–100/mo | Tiny-Live: ~$120–180/mo

## Slide 7
RUNNING COSTS — MONTHLY BREAKDOWN
Compute (t3.medium shadow): $30 | Compute (c6i.large live): $62
Storage S3 500GB: $11 | Monitoring (self): $15 | Networking: $10
Software (LightGBM/NumPy/Sklearn/Streamlit/community): $0–5
Data APIs (Binance/Polymarket/Kalshi): $0
officecli / openpyxl / python-pptx: $0
Base Shadow: ~$65/mo | High Shadow: ~$100/mo | Tiny-Live Low: ~$120/mo | Tiny-Live High: ~$180/mo (with GPU deferred + Datadog)

## Slide 8
TIMELINE — P7 ITERATE → P8 PROMOTION
Week 1–2 — P7.1 Iterate thresholds (sweep 0.30→0.55; turnover reduction; cost-aware sizing)
Week 3 — P7.2 Cost-aware policy + down-model (p_dn_15 producer or safe 0.0 default)
Week 4–5 — P7.3 Shadow validation (2+ weeks live match; latency <2s; 0 errors; replay verified)
Week 6 — P8.1 Paper live (zero real money; JSONL; halt/gate enforced; no dead risk keys)
Week 7 — P8.2 Tiny-live proposal (this PPT + Excel; cost audit; compliance; investor/user approval)
Estimated total: 4–7 weeks

## Slide 9
RISK, GATES & MITIGATION
P4 Quant: PASS — LightGBM AUC 0.637 / ECE 0.01; baselines A–E validated; no leakage (chronological split + purge/embargo)
P7 Cost Survival: FAIL — Net negative at high confidence; 2–3× fees deepen linearly; need lower turnover or cost-aware sizing
P8 Live Match: PASS — Pipeline end-to-end valid; latency 634–1548ms; JSONL hash-verified; consistent with P7 verdict (no entries at p_up~0.13–0.15 vs 0.40 threshold)
Mitigation: Reduce turnover; threshold grid starting 0.30 (446→189,950 fires); wire costs.json into policy; add p_dn_15 before promotion; enforce all RiskConfig keys (remove dead min_depth/max_open until wired)

## Slide 10
CONCLUSIONS & NEXT STEPS
✅ Engineering complete (P0–P6); shadow pipeline validated (P8.1)
❌ Trading edge does NOT survive current cost structure (P7 FAIL) — this is a successful experiment (no false promotion)
➡ Next: Iterate P7 with lower turnover / cost-aware sizing / down-model; re-run hostile 2–3× gate; confirm net positive
➡ Only then: Promote to P8 live paper → tiny-live → proposal / investment / compliance review
Deliverables: PROPOSED_PLAN.md | jev-trading-plan.xlsx (5 sheets) | jev-trading-plan.pptx (10 slides) — all built via officecli v1.0.151 + monid research